## Q4 EAC - Step 1 - Original Budg
Step 1 - Original Budget
Project Phase | ARS Quotation - 1st Part | SCR Resources - 2nd Part | Total Budget
| Original Budget | Original Budget
Requirements Analysis | 150000 | 78400 | 228400
Configuration and Testing | 200000 | 100000 | 300000
User Acceptance Testing | 80000 | 159200 | 239200
Implementation including user training | 50000 | 113600 | 163600
Setup cost for networking and communication | 30000 | - | 30000
| 510000 | 451200 | 961200

## Q4 EAC - Step 2 - Revised Budge
Step 2 - Revised Budget (BAC)
Project Phase | ARS Quotation - 1st Part |  |  | SCR Resources - 2nd Part | Total
| Original Budget | Revised | Revised Budget | Original Budget
Requirements Analysis | 150000 | 5% | 157500 | 78400 | 235900
Configuration and Testing | 200000 | 5% | 210000 | 100000 | 310000
User Acceptance Testing | 80000 | 0 | 80000 | 159200 | 239200
Implementation including user training | 50000 | 0 | 50000 | 113600 | 163600
Setup cost for networking and communication | 30000 | 0 | 30000 | - | 30000
|  |  | 527500 | 451200 | 978700

## Q4 EAC - Step 3 - Budgeted Cost
Step 3 - Budgeted Cost of Work Performed (EV)
Project Phase | ARS Quotation - 1st Part |  |  | SCR Resources - 2nd Part |  |  | Total EV
| Revised Budget (5%) | Percentage Completed | EV | Original Budget | Percentage Completed | EV
Requirements Analysis | 157500 | 100% | 157500 | 78400 | 100% | 78400
Configuration and Testing | 210000 | 80% | 168000 | 100000 | 80% | 80000
User Acceptance Testing | 80000 | 0% | 0 | 159200 | 0% | 0
Implementation including user training | 50000 | 0% | 0 | 113600 | 0% | 0
Setup cost for networking and communication | 30000 | 80% | 24000 | - | - | -
|  |  | 349500 |  |  | 158400 | 507900

## Q4 EAC - Step 4 - Budget Cost o
Step 4 - Budget Cost of Work Scheduled (PV)
Project Phase | ARS Quotation - 1st Part |  |  | SCR Resources - 2nd Part |  |  | Total PV
| Revised Budget (5%) | Percentage Completed | PV | Original Cost | Percentage Completed | PV
Requirements Analysis | 157500 | 100% | 157500 | 78400 | 100% | 78400 | 235900
Configuration and Testing | 210000 | 66.67% | 140000 | 100000 | 66.67% | 66666.6667 | 206666.6667
User Acceptance Testing | 80000 | 0% | 0 | 159200 | 0% | 0 | 0
Implementation including user training | 50000 | 0% | 0 | 113600 | 0% | 0 | 0
Setup cost for networking and communication | 30000 | 66.67% | 20000 | - | - | - | -
|  |  | 317500 |  |  | 145066.6667 | 442566.6667

## Q4 EAC - Step 5 - Actual Cost o
Step 5 - Actual Cost of Work Scheduled (AC)
Project Phase | ARS Quotation - 1st Part |  |  | SCR Resources - 2nd Part |  |  | Total AC
| Revised Budget (8%) | Percentage Completed | AC | Role | Person Months | AC
Requirements Analysis | 162000 | 100% | 162000 | Project Manager | 4 | 86400
Configuration and Testing | 216000 | 80% | 172800 | Business Analyst | 6 | 105600
User Acceptance Testing | 80000 | 0% | 0 | Testers | 0 | 0
Implementation including user training | 50000 | 0% | 0
Setup cost for networking and communication | 30000 | 80% | 24000
|  |  | 358800 |  |  | 192000 | 550800

## Q4 EAC - Step 6 - Expected to c
Step 6 - Expected to complete (ETC)
Project Phase | ARS Quotation - 1st Part |  |  | SCR Resources - 2nd Part |  |  |  | Total ETC
| Revised Budget (8%) | Percentage Uncompleted | ETC | Role | ETC in Person Months | Rate Per Hour | ETC
Requirements Analysis | 162000 | 0% | 0
Configuration and Testing | 216000 | 20% | 43200 | Project Manager | 1 | 135 | 21600
|  |  |  | Business Analyst | 2 | 110 | 35200
User Acceptance Testing | 80000 | 100% | 80000 | Project Manager ($140 from 7th Month) | 1 | 135 | 21600
[5 empty] | 2 | 140 | 44800
|  |  |  | Business Analyst | 1 | 110 | 17600
|  |  |  | Tester | 6 | 80 | 76800
Implementation including user training | 50000 | 100% | 50000 | Project Manager | 2 | 140 | 44800
|  |  |  | Business Analyst | 4 | 110 | 70400
Setup cost for networking and communication | 30000 | 20% | 6000
|  |  | 179200 |  |  |  | 332800 | 512000

## Q4 EAC - SCR Resource Budget Pa
SCR Resource Budget Part.2
.Project Phase | Estimated Effort in Person Months | ARS Quotation - 1st Part | SCR Resources - 2nd Part | [5 empty] | Estimated Elapsed Time in Months
|  | Original Budget | Role | Person Months | Working Housrs(20*8) | Rate Per Hour | Original Subtotal | Original Budget |  | Budget Performed
Requirements Analysis | 4 | 150000 | Project Manager | 2 | 320 | 135 | 43200 | 78400 | 2 | 228400
|  |  | Business Analyst | 2 | 320 | 110 | 35200
Configuration and Testing | 5 | 200000 | Project Manager | 3 | 480 | 135 | 64800 | 100000 | 3 | 300000
|  |  | Business Analyst | 2 | 320 | 110 | 35200
User Acceptance Testing | 10 | 80000 | Project Manager | 3 | 480 | 135 | 64800 | 159200 | 3 | 239200
|  |  | Business Analyst | 1 | 160 | 110 | 17600
|  |  | Testers | 6 | 960 | 80 | 76800
Implementation including user training | 6 | 50000 | Project Manager | 2 | 320 | 135 | 43200 | 113600 | 2 | 163600
|  |  | Business Analyst | 4 | 640 | 110 | 70400
|  | 30000 | [7 empty] | 30000
|  | 510000 | [5 empty] | 451200 |  | 961200

## Q4 EAC - ARS Quotation Part.1-1
ARS Quotation Part.1-1
Role | Person Months | Working Days | Working Hours | Rate Per Hour | Rate
Project Manager | 4 | 20 | 640 | 135 | 86400
Business Analyst | 6 | 20 | 960 | 110 | 105600
Testers | 0 | 20 | 0 | 80 | 0
192000

## Q4 EAC - Project Score Sheet
Project Score Sheet
| Description | Detail
PV | Budgeted cost of work scheduled | 4 months (Complete: Phase 1st = 100%, Phase 2nd and 5th = 2/3 ) | 442566.6667
EV | Budgeted cost of work performed | Complete: Phase 1st = 100%, Phase 2nd and 5th = 80% | 507900
AC | Actual cost of work performed | Money spent | 550800
ETC | Estimate to complete | 6 months left, ARS Budget Revised 8%, SRS Project Manager add $5 per hour from the 7th month | 512000
EAC | Estimate at Completion | AC + ETC | 1062800
BAC | Budget at Completion | My original cost estimate | 978700
SV | Schedule Variance | EV – PV | 65333.3333
SPI | Schedule Performance Index | EV / PV | 114.8%
CV | Cost Variance | EV – AC | -42900
CPI | Cost Performance Index | EV / AC | 92.21%
PC | Percentage Work Completed | EV / BAC | 51.9%
PS | Percentage Money Spent | AC / BAC | 56.28%