## 油盯盯中石化立即加油V1.1
油盯盯中石化加油版 V1.1版本
TIMELINE
PROJECT DETAILS
DATE | MILESTONE | POSITION | BASELINE
2017-06-26 | Planning of requirement analysis activities | 25 | 1
2017-07-15 | Create the framework for future activities | -10 | 1
2017-07-26 | Generate requirements traceability matrix | 12 | 1
2017-08-26 | Review test scripts | -15 | 1
2017-11-26 | Understand the functional of system | 15 | 1
2017-12-20 | Identify User Acceptance business | -20 | 1
2018-01-10 | Create training material | 35 | 1
2018-01-23 | Provide the training to team | -15 | 1
2018-02-05 | Review the test script | 10 | 1
2018-02-10 | Plan go /no go meeting | -10 | 1
2018-02-26 | Create project status report | 20 | 1
2018-03-26 | Perform risk management | -10 | 1
2018-04-10 | Manage change management process | 30 | 1
2018-04-10 | Project End | 40 | 1
Project Timeline Tips:
The role of the Position values in the Project Details table is to prevent the Milestone labels from overlapping each other on the timeline. Use positive numbers to position labels above the timeline and negative numbers to position them below.
To add additional Milestones, either insert new rows within the table or start typing below the last table entry and the table will automatically expand to accommodate your newly added data.